## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Abdullah Waleed bin Maneea |  | 2. Save to one team member's Google drive
Abdullah Yousef aldhayan |  | 3. Share file with other team members
Abdullah Ibrahim aloud |  | 4. Edit First Names on this tab
Fahad Ali alghubayshi |  | 5. Add your team name to the name of this document
6. For each sprint, duplicate the sprint template and change the start date
DOCUMENT HISTORY
| 2026-02-17 | Created by Abdullah bin Maneea

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
1 | US-01 | Define Project Scope and Objectives | As a team, we want to define the project scope and objectives so that all members share a clear understanding of what the system should achieve. | Identify system boundaries, target users, and key goals. | 3-low | Done
1 | US-02 | Identify System Modules and Features | As a team, we want to identify all system modules and features so that the product backlog is comprehensive and well-structured. | Map features to modules: schedule management, reservations, reporting, auth. | 2-medium | Done
1 | US-03 | Create Product Backlog | As a team, we want to create a complete product backlog so that all user stories are listed, prioritized, and ready for sprint planning. | Each story must have an ID, title, description, priority, and sprint assignment. | 1-high | Done
1 | US-04 | Estimate Effort for User Stories | As a team, we want to estimate the effort for each user story so that sprint planning is based on realistic workload. | Assign expected hours to each story; use team consensus. | 2-medium | Done
1 | US-05 | Assign Team Roles and Responsibilities | As a team, we want to assign roles to each member so that responsibilities are clear throughout the project. | Define who leads which module; assign Scrum Master and note-taker. | 1-high | Done
1 | US-06 | Set Up Sprint Sheet and Scrum Template | As a team, we want to set up the Scrum Excel template so that sprint tracking is ready from the start. | Fill in team members, sprint dates, tasks, and hours in the template. | 2-medium | Done
1 | US-07 | Document Team Meetings | As a team, we want to document all group meetings so that progress, decisions, and roadblocks are recorded. | Each meeting entry: date, attendees, agenda, decisions made, next steps. | 3-low | Done
1 | US-08 | Write Project Initiation Report | As a team, we want to write the Phase 1 report so that the project vision, scope, and backlog are formally documented. | Includes cover page, scope, objectives, target audience, and backlog summary. | 3-low | Done
2 | US-09 | Draw Use Case and Sequence Diagrams | As a team, we want to produce use case and sequence diagrams so that system interactions are clearly modeled. | Cover: schedule creation, ticket reservation, cancellation flows. | 3-low | Done
2 | US-10 | Draw Class and Activity Diagrams | As a team, we want to produce class and activity diagrams so that the system structure and logic are documented. | Class diagram covers all entities and relationships; activity covers reservation process. | 3-low | Done
2 | US-11 | Define Architectural Design and Pattern | As a team, we want to define and justify the system architecture so that components and interactions are clearly structured. | Select MVC or Layered Architecture; define components; include architecture diagram. | 2-medium | Done
2 | US-12 | Implement Train Schedule Management | As an admin, I want to create, update, and delete train schedules so that upcoming trips are accurately maintained. | Fields: train ID, route, origin, destination, departure/arrival time, price, capacity. Soft-delete; log changes. | 2-medium | Done
2 | US-13 | Implement Route and Time Definition | As an admin, I want to define routes with departure and arrival times so that full journey details are captured. | Support multiple stops; times stored with timezone info. | 2-medium | In Progress
2 | US-14 | Implement Seat Capacity and Pricing | As an admin, I want to specify seat capacity and pricing per schedule so that availability and cost are tracked. | Capacity tied to train type; pricing can vary by class. | 2-medium | In Progress
2 | US-15 | Implement Passenger Profile Management | As a staff member, I want to register, update, and delete passenger profiles so that passenger data is accurate. | Fields: full name, national ID, date of birth, phone, email. Soft-delete with audit trail. | 1-high | Done
2 | US-16 | Implement Secure Authentication and RBAC | As a user, I want to log in securely and access only what my role permits so that the system is protected. | Password hashing (bcrypt); session expiry; Admin: full access; Staff: reservations and passengers only. | 2-medium | In Progress
2 | US-17 | Submit Initial Implementation with Screenshot | As a team, we want to submit an early running version of the system so that initial progress can be demonstrated. | Include sample code and a screenshot of a working feature inside the Phase 2 report. | 1-high | Done
3 | US-18 | Implement Ticket Reservation and Seat Validation | As a staff member, I want to process reservations and validate seat availability so that overbooking is prevented. | Link passenger to schedule; assign seat; real-time availability check; atomic seat count update. | 2-medium | To Do
3 | US-19 | Implement Ticket Cancellation and Booking Confirmation | As a staff member, I want to cancel tickets and generate booking confirmations so that passengers are properly informed. | Update status to Cancelled; log reason; increment seat count; confirmation includes all booking details. | 3-low | To Do
3 | US-20 | Implement Passenger Booking History | As a staff member, I want to view a passenger's booking history so that I can assist with queries. | Display all past, active, and cancelled reservations per passenger. | 3-low | To Do
3 | US-21 | Implement Admin Dashboard | As an admin, I want to view summary statistics and occupancy rates so that I have a quick operational overview. | Widgets: total trains, bookings today, revenue, active passengers; occupancy % per train. | 2-medium | To Do
3 | US-22 | Implement Reporting and Analytics | As an admin, I want to generate booking and revenue reports so that operational performance is documented. | Daily/weekly/monthly booking reports; revenue breakdown by route/train; utilization rates. Export to PDF/Excel. | 2-medium | To Do
3 | US-23 | Implement Data Validation and Integrity | As the system, I want to enforce data validation and integrity constraints so that only valid data is stored. | Server-side validation for all inputs; foreign key constraints in database. | 1-high | To Do
3 | US-24 | Deploy Web and Mobile Application | As a user, I want to access the system via web and mobile apps so that it is accessible from any device. | Responsive web app; iOS and Android support; cloud deployment with auto-scaling and 99.9% SLA. | 3-low | To Do
3 | US-25 | Implement Backup and Recovery | As an admin, I want automated data backup and recovery so that data is protected against loss. | Daily automated backups; tested restore procedure; 30-day retention policy. | 3-low | To Do
3 | US-26 | Prepare and Execute Test Cases | As a team, we want to prepare and run test cases for all sprints so that system quality is verified. | Test cases for all use cases from sprints 1-3; document pass/fail results in test report. | 3-low | To Do
3 | US-27 | Publish GitHub First Release | As a team, we want to publish the first release on GitHub so that the client can access and run the system. | All members added as collaborators; at least 75% of features functional; include GitHub link in report. | 3-low | To Do
3 | US-28 | Deliver Final Presentation | As a team, we want to deliver a PowerPoint presentation covering all sprints so that our work is demonstrated. | Every member must present and highlight their role in the project. | 2-medium | To Do

## Sprint #1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
US-01 | Define project scope, objectives, and target audience | 2 | 2 | Abdullah Yousef aldhayan | Done |  | Sprint Number: | 1 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2026-02-19 | 0 | 0 | 39 | 39
US-08 | Write Phase 1 initiation report (cover page, scope, vision) | 3 | 2 | Abdullah Yousef aldhayan | Done |  | Start Date: | 2026-02-19 | Abdullah Waleed bin Maneea | 13 | 13 | 100% | 2026-02-20 | 0 | 0 | 39 | 36.2143
US-02 | Identify system modules and map features to each module | 4 | 3 | Abdullah Yousef aldhayan | Done |  | Sprint Length | 14 | Abdullah Yousef aldhayan | 9 | 9 | 100% | 2026-02-21 | 0 | 0 | 39 | 33.4286
US-07 | Document all team meetings (date, agenda, decisions, next steps) | 3 | 3 | Abdullah Waleed bin Maneea | Done |  | Hours Per Day: | 2.7857 | Abdullah Ibrahim aloud | 11 | 11 | 100% | 2026-02-22 | 0 | 0 | 39 | 30.6429
US-03 | Create full product backlog with IDs, priorities, sprint assignment | 6 | 8 | Abdullah Waleed bin Maneea | Done |  |  |  | Fahad Ali alghubayshi | 6 | 6 | 100% | 2026-02-23 | 0 | 0 | 39 | 27.8571
US-04 | Estimate effort (expected hours) for all user stories | 6 | 6 | Fahad Ali alghubayshi | Done |  |  |  |  | 0 | 0 | 0% | 2026-02-24 | 0 | 0 | 39 | 25.0714
US-05 | Assign team roles and responsibilities to each member | 4 | 4 | Abdullah Waleed bin Maneea | Done |  |  |  |  | 0 | 0 | 0% | 2026-02-25 | 0 | 0 | 39 | 22.2857
US-06 | Set up Scrum Excel template: members, dates, tasks, hours | 6 | 7 | Abdullah Ibrahim aloud | Done | [7 empty] | 2026-02-26 | 0 | 0 | 39 | 19.5
US-03 | Create Sprint 1 with IDs, Tasks, Names, Estimated Hours | 5 | 5 | Abdullah Ibrahim aloud | Done |  |  |  | Total: | 39 | 39 | 100% | 2026-02-27 | 0 | 0 | 39 | 16.7143
[13 empty] | 2026-02-28 | 0 | 0 | 39 | 13.9286
[13 empty] | 2026-03-01 | 0 | 0 | 39 | 11.1429
[13 empty] | 2026-03-02 | 0 | 0 | 39 | 8.3571
[13 empty] | 2026-03-03 | 0 | 0 | 39 | 5.5714
[13 empty] | 2026-03-04 | 0 | 0 | 39 | 2.7857
[13 empty] | 2026-03-05 | 0 | 0 | 39 | 0
[14 empty] | 39 | 39 |  | 0
[14 empty] | 39 | 78 |  | 0
[14 empty] | 39 | 117 |  | 0
[14 empty] | 39 | 156 |  | 0
[14 empty] | 39 | 195 |  | 0
[14 empty] | 39 | 234 |  | 0
[14 empty] | 39 | 273 |  | 0
[14 empty] | 39 | 312 |  | 0
[14 empty] | 39 | 351 |  | 0
[14 empty] | 39 | 390 |  | 0
[14 empty] | 39 | 429 |  | 0
[14 empty] | 39 | 468 |  | 0
[14 empty] | 39 | 507 |  | 0
[14 empty] | 39 | 546 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
[14 empty] | 39 | 585 |  | 0
Formulas:
Chart Dates = IFERROR(__xludf.DUMMYFUNCTION("IF(AND(isdate([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, """")"),46073.0)
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Lists (hidden)
Abdullah Waleed bin Maneea | To Do
Abdullah Yousef aldhayan | In Progress
Abdullah Ibrahim aloud | Done
Fahad Ali alghubayshi

## Sprint #2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
US-09 | Draw use case and sequence diagrams for main system flows | 8 | 4 | Abdullah Ibrahim aloud | Done |  | Sprint Number: | 2 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2026-03-05 | 0 | 0 | 66 | 66
US-12 | Implement train schedule CRUD (create, update, soft-delete) | 10 |  | Abdullah Yousef aldhayan | Done |  | Start Date: | 2026-03-05 | Abdullah Waleed bin Maneea | 14 | 14 | 100% | 2026-03-06 | 0 | 0 | 66 | 61.2857
US-10 | Draw class diagram and activity diagram for reservation process | 8 |  | Fahad Ali alghubayshi | Done |  | Sprint Length | 14 | Abdullah Yousef aldhayan | 36 | 36 | 100% | 2026-03-07 | 0 | 0 | 66 | 56.5714
US-13 | Implement route and time definition with multi-stop support | 8 |  | Abdullah Yousef aldhayan | Done |  | Hours Per Day: | 4.7143 | Abdullah Ibrahim aloud | 8 | 8 | 100% | 2026-03-08 | 0 | 0 | 66 | 51.8571
US-11 | Define system architecture (MVC), components, and diagram | 8 |  | Abdullah Waleed bin Maneea | Done |  |  |  | Fahad Ali alghubayshi | 8 | 8 | 100% | 2026-03-09 | 0 | 0 | 66 | 47.1429
US-15 | Implement passenger profile management (register, edit, delete) | 8 |  | Abdullah Yousef aldhayan | Done |  |  |  |  | 0 | 0 | 0% | 2026-03-10 | 0 | 0 | 66 | 42.4286
US-16 | Implement secure login and RBAC (admin/staff roles) | 10 |  | Abdullah Yousef aldhayan | Done |  |  |  |  | 0 | 0 | 0% | 2026-03-11 | 0 | 0 | 66 | 37.7143
US-17 | Submit initial implementation: working code + screenshot in report | 6 |  | Abdullah Waleed bin Maneea | Done | [7 empty] | 2026-03-12 | 0 | 0 | 66 | 33
[5 empty] | To Do |  |  |  | Total: | 66 | 66 | 100% | 2026-03-13 | 0 | 0 | 66 | 28.2857
[5 empty] | To Do | [7 empty] | 2026-03-14 | 0 | 0 | 66 | 23.5714
[5 empty] | To Do | [7 empty] | 2026-03-15 | 0 | 0 | 66 | 18.8571
[5 empty] | To Do | [7 empty] | 2026-03-16 | 0 | 0 | 66 | 14.1429
[5 empty] | To Do | [7 empty] | 2026-03-17 | 0 | 0 | 66 | 9.4286
[5 empty] | To Do | [7 empty] | 2026-03-18 | 0 | 0 | 66 | 4.7143
[5 empty] | To Do | [7 empty] | 2026-03-19 | 0 | 0 | 66 | 0
[5 empty] | To Do | [8 empty] | 66 | 66 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 132 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 198 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 264 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 330 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 396 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 462 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 528 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 594 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 660 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 726 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 792 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 858 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 924 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
[5 empty] | To Do | [8 empty] | 66 | 990 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IFERROR(__xludf.DUMMYFUNCTION("IF(AND(isdate([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, """")"),46087.0)
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint #3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
US-18 | Implement ticket reservation, seat validation, auto seat update | 10 |  | Abdullah Waleed bin Maneea | Done |  | Sprint Number: | 3 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2026-03-19 | 0 | 0 | 98 | 98
US-21 | Implement admin dashboard (summary stats, occupancy rates) | 8 |  | Abdullah Waleed bin Maneea | To Do |  | Start Date: | 2026-03-19 | Abdullah Waleed bin Maneea | 26 | 10 | 38.46% | 2026-03-20 | 0 | 0 | 98 | 91
US-26 | Write and execute test cases for all sprints, document results | 8 |  | Abdullah Waleed bin Maneea | To Do |  | Sprint Length | 14 | Abdullah Yousef aldhayan | 24 | 18 | 75% | 2026-03-21 | 0 | 0 | 98 | 84
US-19 | Implement ticket cancellation and booking confirmation generation | 8 |  | Abdullah Yousef aldhayan | Done |  | Hours Per Day: | 7 | Abdullah Ibrahim aloud | 22 | 14 | 63.64% | 2026-03-22 | 0 | 0 | 98 | 77
US-22 | Implement booking reports and revenue analytics with export | 10 |  | Abdullah Yousef aldhayan | Done |  |  |  | Fahad Ali alghubayshi | 26 | 0 | 0% | 2026-03-23 | 0 | 0 | 98 | 70
US-28 | Prepare and deliver final PowerPoint presentation | 6 |  | Abdullah Yousef aldhayan | To Do |  |  |  |  | 0 | 0 | 0% | 2026-03-24 | 0 | 0 | 98 | 63
US-20 | Implement passenger booking history view | 6 |  | Abdullah Ibrahim aloud | Done |  |  |  |  | 0 | 0 | 0% | 2026-03-25 | 0 | 0 | 98 | 56
US-23 | Implement data validation and database integrity constraints | 8 |  | Abdullah Ibrahim aloud | Done | [7 empty] | 2026-03-26 | 0 | 0 | 98 | 49
US-27 | Publish GitHub first release, add collaborators, verify it runs | 8 |  | Abdullah Ibrahim aloud | To Do |  |  |  | Total: | 98 | 42 | 42.86% | 2026-03-27 | 0 | 0 | 98 | 42
US-24 | Deploy web/mobile app on cloud with auto-scaling and SLA | 10 |  | Fahad Ali alghubayshi | To Do | [7 empty] | 2026-03-28 | 0 | 0 | 98 | 35
US-25 | Implement automated backup and recovery (30-day retention) | 8 |  | Fahad Ali alghubayshi | To Do | [7 empty] | 2026-03-29 | 0 | 0 | 98 | 28
US-14 | Implement seat capacity and class-based pricing per schedule | 8 |  | Fahad Ali alghubayshi | To Do | [7 empty] | 2026-03-30 | 0 | 0 | 98 | 21
[5 empty] | To Do | [7 empty] | 2026-03-31 | 0 | 0 | 98 | 14
[5 empty] | To Do | [7 empty] | 2026-04-01 | 0 | 0 | 98 | 7
[5 empty] | To Do | [7 empty] | 2026-04-02 | 0 | 0 | 98 | 0
[5 empty] | To Do | [8 empty] | 42 | 42 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 84 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 126 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 168 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 210 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 252 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 294 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 336 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 378 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 420 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 462 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 504 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 546 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 588 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
[5 empty] | To Do | [8 empty] | 42 | 630 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IFERROR(__xludf.DUMMYFUNCTION("IF(AND(isdate([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, """")"),46101.0)
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint Template (Make a copy!)
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Brief description |  |  |  | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Start Date: | 2019-03-30 | Abdullah Waleed bin Maneea | 0 | 0 | 0% | 2019-03-31 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Sprint Length | 14 | Abdullah Yousef aldhayan | 0 | 0 | 0% | 2019-04-01 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Hours Per Day: | 0 | Abdullah Ibrahim aloud | 0 | 0 | 0% | 2019-04-02 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Fahad Ali alghubayshi | 0 | 0 | 0% | 2019-04-03 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-04 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-05 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-06 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Total: | 0 | 0 | 0% | 2019-04-07 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-08 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-09 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-10 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-11 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-12 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-13 | 0 | 0 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = IFERROR(__xludf.DUMMYFUNCTION("IF(AND(isdate([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, """")"),43555.0)
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")